**Planning timeline for Erie County parish restructuring**

**Preliminary plan is unveiled** August 29

* Ongoing discussion and prayer at the parish level

**Feedback on the preliminary plan surveys due** September 29

* Pastoral Planning Committee develops final plan

**Bishop Persico brings the final plan proposal to**

**Presbyteral Council**  End of November

**Adjustments to the proposed final plan are finalized**

**and brought to Presbyteral Council for final review** February 2024

* Ongoing discussion with pastors/assignments

**Final plan is made public** April 2024

**Final plan is implemented** June/July 2024